# 14 day presentation timeline

Replace day numbers with dates and move submission earlier when required. Check each output before marking it done.

| Day | Milestone | Owner | Output |
| --- | --- | --- | --- |
| 1 | Agree on brief, availability, roles | Maya coordinates; all confirm | Approved one-page plan |
| 2 | Divide research questions and source needs | Jordan coordinates | Research map with named owners |
| 3-4 | Read and record evidence | Each student | Source notes posted by day 4 |
| 5 | Approve the argument and slide outline | Maya; all review | One agreed 10-slide outline |
| 6-7 | Draft assigned slides and speaking notes | Each student | Complete sections by day 7 |
| 8 | Assemble one consistent master deck | Elena | Whole deck ready for review |
| 9 | Review claims, citations, and rubric | Jordan coordinates; review partners check | Specific correction list |
| 10 | Resolve the review findings | Each owner; Elena integrates | Revised deck |
| 11 | First timed group rehearsal | Maya tracks time; all speak | Timing and transition notes |
| 12 | Second rehearsal and technology check | Elena handles slides; all rehearse | Checked delivery and backup plan |
| 13 | Export, reopen, submit, verify receipt | Elena submits; Jordan verifies | Correct file and submission confirmation |
| 14 | Present and answer questions | All three | Final presentation |

# Your presentation schedule

Fill dates and owners. Complete means the output is available and reviewed.

| Done | Date | Milestone | Owner | Output | Reviewer |
| --- | --- | --- | --- | --- | --- |
| [ ] |  | Brief and roles |  |  |  |
| [ ] |  | Research map |  |  |  |
| [ ] |  | Source notes |  |  |  |
| [ ] |  | Outline approved |  |  |  |
| [ ] |  | Slide drafts |  |  |  |
| [ ] |  | Master deck |  |  |  |
| [ ] |  | Peer review |  |  |  |
| [ ] |  | Revisions |  |  |  |
| [ ] |  | Rehearsal 1 |  |  |  |
| [ ] |  | Rehearsal 2 |  |  |  |
| [ ] |  | Export and submit |  |  |  |
| [ ] |  | Present |  |  |  |

Upload deadline ________________   Presentation date ________________